## Weekly Gantt Chart Template
WEEKLY GANTT CHART
| PROJECT: |  | SOCIAL MEDIA TREND ANALYZER
| Project Manager: |  | Suzan Üsküdarlı
[5 empty] | 2020-10-27 | 2020-11-03 | 2020-11-10 | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2020-12-15 | 2020-12-22 | 2020-12-29 | 2021-01-05 | 2021-01-12 | 2021-01-19 | 2021-01-26 | 2021-02-02 | 2021-02-09
Task name | Stard date | End date | Assigned | Progress | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16
PROJECT 1 | 2020-10-27 | 2020-01-20 | Ulaş | 40%
Task 1: Project Setup | 2020-10-27 | 2020-11-07 | Ulaş | 100%
Subtask 1.1: Create GitHub Repo | 2020-10-27 | 2020-11-02 | Ulaş | 100%
Subtask 1.2: Wikidata Research | 2020-10-27 | 2020-11-07 | Ulaş | 100%
Task 2: Requirement Elicitation | 2020-11-03 | 2020-11-09 | Ulaş | 100%
Task 3: SRS Document | 2020-11-10 | 2020-11-23 | Ulaş | 100%
Task 4: Software Design | 2020-11-24 | 2020-12-07 | Ulaş | 50%
Task 5: Data Acquisition Using API | 2020-12-01 | 2020-12-07 | Ulaş | 20%
Task 6: Entity Linking | 2020-12-08 | 2020-12-14 | Ulaş | 0%
Task 7: Usage of Docker | 2020-12-07 | 2020-12-21 | Ulaş | 0%
Task 8: Implementation of Backend Design | 2020-12-07 | 2020-12-28 | Ulaş | 0%
Task 9: Implementation of Frontend Design | 2020-12-28 | 2021-01-15 | Ulaş | 0%

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "D" and "E" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change LOGO image, right click on it and choose CHANGE PICTURE.

## ©
© TemplateLab.com